## Cover
ClearLedger Advisory
SSC Transition
Guide
TOOLKIT 2.0 · PROCESS OPTIMIZATION SERIES
APQC PCF v8.0 aligned · Templates · Frameworks · Benchmarks
DOCUMENT INFORMATION
Prepared for | [Client Name]
Prepared by | [Consultant Name]
Engagement date | [Date]
Version | 1.0
License | Single-entity commercial license
WHAT'S INSIDE
Shared-services transition framework: phased roadmap, scope assessment, location analysis, and KPI scorecard for migrating OtC processes to an SSC/GBS model.
CONTENTS
01 | Transition Roadmap | Transition Roadmap
02 | Scope Assessment | Scope Assessment
03 | Location Analysis | Location Analysis
04 | KPI Scorecard | KPIs · APQC v8.0 benchmarks · RAG status
APQC PCF v8.0: Shared Services Transition

## Instructions
How to Use This Pack
Follow these steps from diagnostic to deployment
Step 1 | Assess Scope
Use Scope Assessment to determine what to transition.
Step 2 | Select Location
Use Location Analysis with weighted criteria.
Step 3 | Plan Transition
Use Transition Plan as your project roadmap.
Step 4 | Set SLAs
Define SLAs using the framework.
▸ Blue cells are inputs you edit. Black values are formula-driven — do not overtype them.

## Transition Roadmap
SSC Transition Roadmap — Phase 0 to 4
End-to-end framework for OtC SSC transition
Phase | Duration | Activities | Deliverables | Key Milestone
0 — Assess | 4-6 wk | Assess current state, benchmark, define scope, build business case | Transition charter, business case, scope doc | Gate 0 — Charter Approved
1 — Design | 6-8 wk | Design target process, select tech, build RACI, develop SLAs | Process maps, tech stack, SLA definitions | Gate 1 — Design Signed Off
2 — Build | 8-12 wk | Hire/transfer staff, configure systems, build KB, run pilots | Staffed team, system ready, KB library | Gate 2 — Pilot Complete
3 — Cutover | 4-6 wk | Cutover in waves, parallel run, exception handling | Cutover plan, exception protocols | Gate 3 — Cutover Complete
4 — Stabilise | 8-12 wk | Stabilisation, CI, KPI monitoring, governance setup | Stabilisation report, CI roadmap | Gate 4 — Steady State

## Scope Assessment
SSC Scope Assessment Matrix
Score 1-5. Blue = editable.
Sub-Process | Complexity | Volume | Automation | SSC Fit | Score | Rationale
Cash App — Auto-Match | 1 | 5 | 5 | High | 15 | High volume, rules-based, low judgment
Cash App — Exceptions | 3 | 3 | 4 | Medium | 10 | Requires analyst judgment
Invoice Generation | 1 | 5 | 5 | High | 15 | Fully automatable
Invoice Delivery | 1 | 5 | 5 | High | 15 | Auto via Peppol/EDI/portal
Credit/Debit Memo | 2 | 3 | 3 | High | 10 | Rule-based with approval workflow
Credit Management | 3 | 2 | 3 | Medium | 8 | Analytical but processable
Collections — Auto Dunning | 1 | 5 | 5 | High | 15 | Segmented auto-workflow
Collections — High-touch | 4 | 1 | 2 | Medium/Low | 5 | Relationship-based
Dispute Intake | 2 | 3 | 3 | High | 10 | Auto triage via portal
Dispute Investigation | 3 | 3 | 2 | Medium | 8 | Requires knowledge base
Dispute Resolution | 4 | 2 | 1 | Low | 5 | Judgment-intensive
AR Reporting | 2 | 3 | 4 | High | 11 | Automated dashboards

## Location Analysis
Location Scoring Model
Score 1-10. Blue = editable. Weighted total auto-calculated.
Factor | Weight | Option 1 | Option 2 | Option 3 | Option 4 | W Score 1 | W Score 2
Labour Cost | 0.2 |  |  |  |  | 0 | 0
Talent Availability | 0.2 |  |  |  |  | 0 | 0
Language Skills | 0.15 |  |  |  |  | 0 | 0
Infrastructure | 0.15 |  |  |  |  | 0 | 0
Time Zone Overlap | 0.1 |  |  |  |  | 0 | 0
Legal/Regulatory | 0.1 |  |  |  |  | 0 | 0
Business Climate | 0.05 |  |  |  |  | 0 | 0
Cultural Fit | 0.05 |  |  |  |  | 0 | 0
TOTAL | [5 empty] | 0 | 0

## KPI Scorecard
KPI Scorecard — SSC Transition
Blue = editable
KPI | Current | Target | Top | Median | Bottom | Status | APQC | Definition
Transition Timeline (months) | 9 | 6 | 4 | 7 | 12 | ● On Target | 4.2.1 | Assess to steady state
Cost Savings Realised (%) | 15 | 25 | 35 | 22 | 12 | ● On Target | 4.2.2 | (Baseline - New) ÷ Baseline
SLA Achievement (%) | 82 | 95 | 98 | 88 | 75 | ● Off Target | 4.2.3 | SLAs met ÷ Total SLAs
Knowledge Transfer (%) | 70 | 95 | 98 | 85 | 65 | ● Off Target | 4.2.4 | KB documented ÷ Required
Staff Attrition — Provider (%) | 18 | 10 | 8 | 15 | 25 | ● On Target | 4.2.5 | Provider staff turnover
First-Year Retention (%) | 85 | 95 | 98 | 90 | 75 | ● Off Target | 4.2.6 | Customers retained post-transition
Volume Ramp (%) | 75 | 90 | 100 | 85 | 65 | ● Off Target | 4.2.7 | Planned vs actual volume ramp
Governance Satisfaction | 3 | 4.5 | 4.8 | 4 | 3 | ● Off Target | 4.2.8 | Survey score 1-5
RAG status compares Current vs Target (direction-aware). Edit blue cells to update.

## Lists (hidden)
SSC Fit | Phase Status | Risk Level
High | Not Started | Low
Medium | In Progress | Medium
Medium/Low | Complete | High
Low | On Hold | Critical